## Sheet1
ID | Story | As a ... | I want ... | so that... | Acceptance Criteria | PRIORITY 1 - Business Value | PRIORITY 2- User Impact | PRIORITY - TOTAL | ESTIMATION
1 | create an account | unregistered user | to create an accout | I can have an account | when user clicks register button, it takes them to new page where they will fill out needed information | 5 | 5 | 25 | 2
2 | log in | registered user | to login with my account | I can put up my car for sale | when user logs in with their information, they are able to access their account and are able to publish a car sale | 5 | 5 | 25 | 1
3 | edit account info | registered user | to edit my account | I can update my personal information | when user clicks edit account button, they are able to edit/change their personal information | 5 | 5 | 25 | 3
4 | create database for users | system | to have a database | I can store all information about users | when user creates an account, the system stores that information | 4 | 5 | 20 | 2
5 | create database for cars | system | to have a database | I can store all information about cars | when user adds a car to sell, the system stores that car listing | 4 | 5 | 20 | 3
6 | scroll through car sales | unregistered user | to look at car sales without being logged in | I can choose a car without creating an account | when unregistered user accesses the site, they are able to see all the contents withoutthem being logged in or having an account | 3 | 4 | 12 | 5
7 | publish a car sale | registered user | to post a car sale | I can sell my car | when registered user is logged in, they are able to post a car sale | 3 | 4 | 12 | 5
8 | search for cars | registered/unregistered user | to search for cars | I can potentially find the right one | both registered and unregistered users are able to search for cars | 3 | 3 | 9 | 3
9 | search details | registered/unregistered user | to search for cars | I can potentially find the right one | search details include make, model, year, type, price, fuel type, kilometers, transmission, fuel type etc. | 3 | 4 | 12 | 5
10 | publish a car sale | registered user | to post a car sale | I can sell my car | when publishing a car sale, the user is able to choose from all of the details above and add their own information in a more details box | 2 | 3 | 6 | 5
11 | scroll through car sales | registered/unregistered | to search for cars | I can potentially find the right one | when user is scrolling, they are able to choose in which orded the cars are displayed in | 2 | 2 | 4 | 4
12 | opening one car sale | registered/unregistered | to open car listing | I can see more info about the car | when user opens a car listing, they are able to see car photos and car information in details and information about the car seller, where they are located and their contact information | 1 | 3 | 3 | 2
13 | administrator job | administrator | to access information about the site | I can constantly update the site | administrator job is to maintain site links and work as a backup for the Web Security Administrator, work with UI/UX developers to validate that standards are being met across the company's intranet | 1 | 2 | 2 | 1